## Go-Live Readiness
ID | Priority | Category | Item | Description | Owner | Effort | Status | % Complete | Target Date | Notes / Blockers
CRIT-01 | 🔴 CRITICAL | Security | Penetration test | Hire CREST/CHECK-certified pen tester to test auth bypass, IDOR, SQL injection, XSS, API rate limiting, health data leakage |  | 1-2 weeks | Not Started | 0 |  | Budget ~£3-5k
CRIT-02 | 🔴 CRITICAL | Legal / GDPR | Data Protection Impact Assessment (DPIA) | Required under UK GDPR Article 35 for processing special category health data at scale. Must cover lawful basis, data minimisation, retention, international transfers, AI automated decision-making |  | 1 week | Not Started | 0
CRIT-03 | 🔴 CRITICAL | QA | Run full QA test pack | Execute all 381 test cases in docs/MeticleCare_QA_UAT_Test_Pack.xlsx. Fill in Pass/Fail and Comments. Return for bug fixes |  | 3-5 days | Not Started | 0
CRIT-04 | 🔴 CRITICAL | Security | SSL certificates verified | Verify production has valid SSL certs with auto-renewal configured. Test HTTPS on all endpoints |  | 1 hour | Not Started | 0
CRIT-05 | 🔴 CRITICAL | Data | Backup & recovery testing | Perform test database restore from backup. Verify data integrity. Document RTO/RPO. Test point-in-time recovery |  | 1 day | Not Started | 0
CRIT-06 | 🔴 CRITICAL | Infrastructure | Database connection pooling verified | Verify PgBouncer or equivalent is configured. Test connection pool exhaustion under load. Set up connection pool monitoring |  | Half day | Not Started | 0
CRIT-07 | 🔴 CRITICAL | Legal / GDPR | DPIA reviewed by DPO or legal counsel | The DPIA document must be reviewed and signed off by a qualified Data Protection Officer or solicitor before launch |  | 1-2 days | Not Started | 0
HIGH-01 | 🟠 HIGH | Legal / GDPR | ICO registration | Register as data controller with ICO (ico.org.uk). Required if processing personal data. Currently £40-60/year for small orgs |  | 1 hour | Not Started | 0
HIGH-02 | 🟠 HIGH | Monitoring | Uptime monitoring & alerting | Set up uptime monitoring (UptimeRobot, Betterstack, or similar). Configure alerts for API downtime, high error rates, database issues, disk space |  | 2-3 hours | Not Started | 0
HIGH-03 | 🟠 HIGH | Legal | Solicitor review — Terms of Use | Have a solicitor review Terms of Use for enforceability, limitation of liability, indemnification clauses specific to health/social care software |  | 1-2 weeks | Not Started | 0
HIGH-04 | 🟠 HIGH | Legal | Solicitor review — Privacy Policy | Review Privacy Policy for UK GDPR compliance. Ensure lawful basis for processing health data is clearly documented. Verify data subject rights are covered |  | 1-2 weeks | Not Started | 0
HIGH-05 | 🟠 HIGH | Legal | Create standalone DPA document | The Terms of Use references a Data Processing Agreement. Create a standalone DPA for care homes signing up as data controllers |  | 3-5 days | Not Started | 0
HIGH-06 | 🟠 HIGH | Legal | Cookie policy accuracy review | Verify Cookie Policy accurately reflects all cookies used. Update if any analytics or tracking is added post-launch |  | 2 hours | Not Started | 0
HIGH-07 | 🟠 HIGH | Insurance | Professional indemnity insurance | Obtain PI insurance covering software defects that could cause harm in a care setting. Also consider cyber liability insurance for data breach |  | 1 week | Not Started | 0
HIGH-08 | 🟠 HIGH | Infrastructure | Redis configured for Socket.IO | Verify Redis adapter is configured for horizontal scaling of real-time features (chat, notifications, mission control). Test with multiple API instances |  | Half day | Not Started | 0
HIGH-09 | 🟠 HIGH | Security | API key rotation policy | Implement or document a policy for rotating API keys (OpenAI, Anthropic, Stripe). Set calendar reminders for quarterly rotation |  | 2 hours | Not Started | 0
HIGH-10 | 🟠 HIGH | Security | Rate limiting verified in production | Verify rate limits are applied to all public-facing endpoints. Test with concurrent requests to confirm 429 responses |  | 2 hours | Not Started | 0
MED-01 | 🟡 MEDIUM | Compliance | CQC registration guidance | Clarify whether MeticleCare needs CQC registration (only if providing care directly) or if it is purely software for care providers |  | Research | Not Started | 0
MED-02 | 🟡 MEDIUM | Operations | Incident response plan | Document what happens when: data breach occurs, system goes down, safeguarding concern arises. Who to call, what to do, comms templates |  | 2-3 days | Not Started | 0
MED-03 | 🟡 MEDIUM | Operations | Staff onboarding documentation | Create internal docs for any team members who will support the platform: how to access logs, how to reset users, how to check billing |  | 1-2 days | Not Started | 0
MED-04 | 🟡 MEDIUM | Infrastructure | Production environment audit | Review docker-compose.prod.yml, verify all services have health checks, proper resource limits, log rotation, and restart policies |  | Half day | Not Started | 0
MED-05 | 🟡 MEDIUM | Data | Data retention policy implementation | Ensure the app enforces data retention periods. Health data retention per NHS records management code of practice. Implement auto-deletion or archival |  | 2-3 days | Not Started | 0
MED-06 | 🟡 MEDIUM | AI | AI content labelling audit | Verify all AI-generated outputs (daily notes, meal plans, incident triage, compliance analysis) are clearly labelled as AI-generated in the UI and database |  | 1 day | Not Started | 0
MED-07 | 🟡 MEDIUM | Operations | Disaster recovery runbook | Document step-by-step recovery procedures: database restore, service restart, DNS failover, data integrity checks. Test the runbook |  | 1-2 days | Not Started | 0
MED-08 | 🟡 MEDIUM | Accessibility | WCAG 2.1 AA compliance audit | Run axe-core or similar against key pages. Fix critical violations (missing alt text, colour contrast, keyboard navigation, screen reader support) |  | 2-3 days | Not Started | 0
LOW-01 | 🟢 LOW | Performance | Load testing | Run k6 or Artillery against the API. Simulate 50, 100, 200 concurrent users. Measure response times, error rates, and resource usage |  | 1-2 days | Not Started | 0
LOW-02 | 🟢 LOW | Infrastructure | Domain & DNS setup | Finalise production domain. Configure DNS records. Set up email sending (SPF/DKIM/DMARC for transactional emails) |  | 2-3 hours | Not Started | 0
LOW-03 | 🟢 LOW | Operations | Customer support process | Define how support tickets are handled: email, chat, phone. Who responds. SLA targets. Escalation path for urgent issues |  | Half day | Not Started | 0
LOW-04 | 🟢 LOW | Compliance | CQC evidence pack auto-generation test | Verify evidence packs generate correctly with real data. Test all CQC domains (Safe, Effective, Caring, Responsive, Well-led) |  | Half day | Not Started | 0
LOW-05 | 🟢 LOW | Marketing | Landing page A/B test plan | Plan initial A/B tests for the landing page: headline variations, CTA placement, pricing display, trust strip positioning |  | Half day | Not Started | 0
LOW-06 | 🟢 LOW | Documentation | API documentation | Generate or write API docs for any public-facing or integration APIs. Consider OpenAPI/Swagger spec generation |  | 2-3 days | Not Started | 0
LOW-07 | 🟢 LOW | Marketing | Social proof & testimonials | Collect early beta user feedback. Create case studies or testimonials. Add to landing page once available |  | Ongoing | Not Started | 0

## Summary
Priority | Total | Not Started | In Progress | Blocked | Complete | % Complete
🔴 CRITICAL | 7 | 7 | 0 | 0 | 0 | 0%
🟠 HIGH | 10 | 10 | 0 | 0 | 0 | 0%
🟡 MEDIUM | 8 | 8 | 0 | 0 | 0 | 0%
🟢 LOW | 7 | 7 | 0 | 0 | 0 | 0%
TOTAL | 32 | 32

## By Category
Category | Total Items | Critical | High | Medium | Low
Security | 4 | 2 | 2 | 0 | 0
Legal / GDPR | 3 | 2 | 1 | 0 | 0
QA | 1 | 1 | 0 | 0 | 0
Data | 2 | 1 | 0 | 1 | 0
Infrastructure | 4 | 1 | 1 | 1 | 1
Monitoring | 1 | 0 | 1 | 0 | 0
Legal | 4 | 0 | 4 | 0 | 0
Insurance | 1 | 0 | 1 | 0 | 0
Compliance | 2 | 0 | 0 | 1 | 1
Operations | 4 | 0 | 0 | 3 | 1
AI | 1 | 0 | 0 | 1 | 0
Accessibility | 1 | 0 | 0 | 1 | 0
Performance | 1 | 0 | 0 | 0 | 1
Marketing | 2 | 0 | 0 | 0 | 2
Documentation | 1 | 0 | 0 | 0 | 1

## Timeline
Week | Focus Area | Key Items | Status | Notes
Week 1 | Security & Legal | Engage pen tester, begin DPIA draft, ICO registration, SSL verification | Not Started
Week 2 | QA & Testing | Run full QA test pack (381 cases), document all failures, begin load testing | Not Started
Week 3 | Legal & Compliance | DPIA review by DPO, solicitor review of Terms + Privacy Policy, create DPA document | Not Started
Week 4 | Infrastructure & Monitoring | Uptime monitoring setup, backup recovery testing, Redis scaling test, prod audit | Not Started
Week 5 | Bug Fixes & Polish | Fix all QA failures, address pen test findings, AI labelling audit, WCAG fixes | Not Started
Week 6 | Launch Prep | Final smoke test, incident response runbook, monitoring live, disaster recovery test | Not Started